## Sheet1
Mobile Plan Planning (Defenders)
Epic | Epic Name | Ticket ID | User Stories | Assigned To | Status | Start Date | End Date | Duration (In day)
1 | Rest API Creation in Spring Boot Application | MP-1 | Read By id Controller | Aishwarya | Done | 2022-08-25 | 2022-08-25 | 1
|  | MP-2 | Read All Controller | Roshani | Done | 2022-08-25 | 2022-08-25 | 1
|  | MP-3 | Update Controller | Pratik | Done | 2022-08-26 | 2022-08-29 | 2
|  | MP-4 | Delete Controller | Amey | Done | 2022-08-26 | 2022-08-29 | 2
|  | MP-5 | Update & Delete Service | Surbhit | Done | 2022-08-26 | 2022-08-29 | 2
2 | UI and It's integration with Spring boot Application | MP-6 | Home Webpage & Search By id Webpage | Aishwarya | Done | 2022-08-26 | 2022-09-01 | 4
|  | MP-7 | Create Webpage & Delete By id Webpage | Roshani | Done | 2022-09-01 | 2022-09-02 | 2
|  | MP-8 | Update Webpage & View All Webpage | Pratik | Done | 2022-09-01 | 2022-09-02 | 2
|  | MP-9 | Integration of Front end & Backend | Surbhit & Amey | Done | 2022-09-01 | 2022-09-02 | 2
|  | MP-10 | About Us webpage | All | Done | 2022-09-01 | 2022-09-02 | 2
3 | UI Improvement & Added Features | MP-11 | Improvement in Homepage | Aishwarya | Done | 2022-09-06 | 2022-09-07 | 2
|  | MP-12 | Alerts | Surbhit | Done | 2022-09-06 | 2022-09-07 | 2
|  | MP-13 | About Us webpage | Pratik | Done | 2022-09-06 | 2022-09-07 | 2
|  | MP-14 | Improvement in View All webpage | Roshani | Done | 2022-09-06 | 2022-09-07 | 2
|  | MP-15 | Added Required Field in Frontend | Amey | Done | 2022-09-06 | 2022-09-07 | 2
4 | Documentation & Testcases | MP-16 | Postman JSON Collection | Aishwarya | Done | 2022-09-08 | 2022-09-09 | 2
|  | MP-17 | Test Cases(+ve & -ve) | Pratik & Roshani | Done | 2022-09-08 | 2022-09-09 | 2
|  | MP-18 | Docker File and Documentation | Amey | Done | 2022-09-09 | 2022-09-12 | 2
|  | MP-19 | ER Diagram and other UML Diagrams | Surbhit | Done | 2022-09-09 | 2022-09-12 | 2
5 | Improvement in Documentation & UI | MP-20 | Update ER digram | Pratik | Done | 2022-09-13 | 2022-09-13 | 1
|  | MP-21 | Improvement in about us | Roshani | Done | 2022-09-13 | 2022-09-13 | 1
|  | MP-22 | Validations of Mandatory Field | Surbhit | Done | 2022-09-14 | 2022-09-15 | 2
|  | MP-23 | Added more test cases | Aishwarya | Done | 2022-09-15 | 2022-09-16 | 2
|  | MP-24 | Added Index Page in Report | Amey | Done | 2022-09-15 | 2022-09-16 | 2
6 | UI Testing & Improvement | MP-25 | Correction in numeric fields | Surbhit | Done | 2022-09-19 | 2022-09-20 | 2
|  | MP-26 | Added more test cases | Aishwarya | Done | 2022-09-19 | 2022-09-20 | 2
|  | MP-27 | More improvements in UI | Amey | Done | 2022-09-19 | 2022-09-20 | 2
|  | MP-28 | Tested fields in UI | Pratik & Roshani | Done | 2022-09-19 | 2022-09-20 | 2
7 | Overall Changes in Mobile Plan & Report | MP-29 | Improved indentations | Surbhit | Done | 2022-09-21 | 2022-09-22 | 2
|  | MP-30 | Added Test Cases Other than Services | Aishwarya | Done | 2022-09-21 | 2022-09-22 | 2
|  | MP-31 | Changes in Homepage | Roshani | Done | 2022-09-21 | 2022-09-22 | 2
|  | MP-32 | Improvement In MobilePlan Report | Amey & Pratik | Done | 2022-09-21 | 2022-09-22 | 2